Project Charter: Rollout of tabletop menu tablets

DATE: [25/02/25]

Project Summary

launch a pilot rollout of tabletop menu tablets at two of our restaurant locations, Sauce & Spoon North and Sauce & Spoon Downtown. That way, guests can place their orders on the tablets as soon as they arrive at the restaurant, rather than waiting for a server to attend to them.

Project Goals

● Increase the average check from $65 to $75 by improving product mix and boosting appetizer sales by 15%. ● Introduce a digital ordering system and train staff thoroughly to ensure a smooth and efficient transition. ● Make sure both the front of house and kitchen are properly staffed to handle a 10% rise in daily guest volume and to reduce staff burnout and turnover. ● Cut table turn time by 30 minutes, helping to reduce guest wait times and serve more customers each day. ● Set clear data points to track key metrics and measure progress effectively. ● Reduce meal comps by cutting down on food send-backs (exact % TBD) and lowering food waste by 25%. ● Work on increasing customer satisfaction (target % TBD) through improved service and food quality.

Deliverables

● Achieve a 15% overall increase in appetizer orders, aiming for a 10% rise at the North location and a 20% increase at the Downtown location. ● Reduce average table turn time by 30 minutes to improve guest flow and seating efficiency. ● Raise the average check to $75 by increasing appetizer and beverage sales, leading to higher overall profits. ● Grow the average number of daily guests by 10%. ● Roll out a staff training program to enhance service and operational consistency. ● Improve communication of special guest requests to the kitchen to lower meal comps and cut food waste by 25%. ● Ensure smooth integration with the current POS system for streamlined operations

Scope and Exclusion

In-Scope ● Reducing food waste and minimizing order return rates ● Improving employee satisfaction and engagement ● Increasing average check total ● Shortening table turn time ● Boosting the average number of daily guests ● Implementing effective staff training programs ● Ensuring seamless integration with the current POS system Out-of-Scope: - Policy change

Benefits & Costs

Benefits: ● Tablets will offer valuable insights into customer ordering habits and work seamlessly with the POS system to support informed decision-making going forward ● Cutting down on food waste ● Increase profits. ● Increase overall customer experience ● Increasing employee satisfaction Costs: - Training material fees: $10,000 - Hardware and Software implementation across locations: $30,000 - Maintenance (IT fees through EOY): $5,000 ● Website and menu design updates: $5,000 ● Additional customization costs: $55

Appendix:

● Payroll Reallocation Peta was hesitant to shift payroll to BOH without data on staffing needs. Deanna and Alex supported planning for BOH resources, while Gilly opposed reducing FOH payroll. Decision: Unresolved—will revisit later. ● Appetizer Sales Target Alex felt an increase wouldn’t impact his location much due to existing happy hour traffic. Gilly pushed for a higher target based on her location’s low app sales. Decision: Agreed on a 15% average increase—10% for North, 20% for Downtown. ● Policy Change Debated whether to include policy changes in scope. Decision: Out of scope—will handle separately. ● Employee Satisfaction Debate on including employee satisfaction measurement. Decision: Carter and Deanna to develop a tracking method.