## Slide 1
Stakeholder | Role | Power (H/M/L) | Interest (H/M/L) | Notes
Omar Mubarak | Owner | H | M | ● Responsible for the overall direction, profitability, andr reputation of the restaurant group. ● Senior most stakeholder.
Deanna Coleman | Director of Operations | H | H | ● Responsible for daily communication across different teams. ● Oversees the restaurant managers. ● Helps with interviewing, hiring, and training new employees.
Carter Ward | Executive Chef | M | H | ● Has the final say on all menu choices. ● Responsible for overseeing all other chefs employed by the restaurant.
Gilly Tyson | General Manager (North) | H | H | ● Great resource for training and providing input on general restaurant operations. ● Responsible for hiring and training staff, ordering all the restaurant’s supplies, and gauging customer satisfaction at location
Alex Schmidt | General Manager (Downtown) | H | H | ● Previously worked in retail management at a large home improvement chain. ● Trained by Gilly. ● Responsible for hiring and training staff, ordering all the restaurant’s supplies, and gauging customer satisfaction at location
Stakeholder Analysis

## Slide 2
Stakeholder | Role | Power (H/M/L) | Interest (H/M/L) | Notes
Nia Williams | General Manager (Waterfront) | L | L | ● Experience from hostess up to management. ● Tended bar at a luxury hotel which would be helpful for the pilot. ● Passionate about the restaurant industry. ● Responsible for hiring and training staff, ordering all the restaurant’s supplies, and talking to customers to ensure that they are happy with their service.
Zane Dutchman | Kitchen Manager (North) | M | H | ● Sous chef before kitchen manager - enthusiastic about role ● Learning from Larissa. ● Responsible for: (1) Overseeing daily BOH operations and administrative tasks and (2) Controlling costs and managing labor.
Larissa Stein | Kitchen Manager (Downtown) | M | H | New to Sauce & Spoon. ● Previously managed kitchen at a Michelin-star restaurant. ● Enthusiastic about role and restaurant work. ● Responsible for: (1) Overseeing daily BOH operations and administrative tasks and (2) Controlling costs and managing labor.
Seydou Diallo | Restaurant Technology Consultant | M | H | ●Background in tech support and new to restaurant industry. ● First major project and excited to prove himself. ● Helps restaurants implement cost-effective, easy-to-use, integrated technology systems.
Stakeholder Analysis

## Slide 3
Keep satisfied (high priority)
Manage closely (high effort)
Monitor (minimum effort)
Show consideration
Power
high
low
med
high
low
Omar
Owner
Deanna
Director of Operations
Carter
Exec. Chef
Gilly
GM - North
Alex
GM - Downtown
Zane
Kitchen Manager - North
Larissa
Kitchen Manager - Downtown
Seydou
Restaurant Consultant
Interest
med
Nia
General Manager - Waterfront